## CIBIS9
COST
| PHASE | CODE | TASK | BUDGET | ALL YEAR | 2010 | 2011 | 2012 | 2013 | 2014 | 2015
Soft Cost | Feasibility Study | 0.A | Appraisal Work |  | 0
|  | 0.B | Feasibility Study |  | 0
| Master Planning | 1.A | Concept and Schematic | 1726774700 | 1566300000 |  |  |  | 1566300000
| Design Development | 2.A | Consept Design |  | 679000000 |  |  |  | 679000000
|  | 2.B | Planning Development Stage |  | 0
|  | 2.C | Tender Document Stage |  | 0
|  | 2.D | Construction Stage |  | 0
| Infrastructure | 3.A | Consept Design | 750000000 | 0
|  | 3.B | Planning Development Stage |  | 0
|  | 3.C | Tender Document Stage |  | 0
|  | 3.D | Construction Stage |  | 0
| Façade | 4.A | Schematic Design Stage | 900000000 | 0
|  | 4.B | Design Developemnt stage | 2731520000 | 0
|  | 4.C | Tender Documentation Stage |  | 0
|  | 4.D | Tender Stage |  | 0
|  | 4.E | Performance Mock-Up Stage |  | 0
|  | 4.F | Shop drawing & Engineering Review Stage |  | 0
|  | 4.G | Fabrication and Installation Stage |  | 0
|  | 4.H | Hand - Over Stage |  | 0
| Structure and Civil Engineering | 5.A | Consept Design | 900000000 | 212500000 |  |  |  | 212500000
|  | 5.B | Planning Development Stage |  | 0
|  | 5.C | Tender Document Stage |  | 0
|  | 5.D | Construction Stage |  | 0
| Mechanical, Electrical and Plumbing | 6.A | Design Concept | 970000000 | 291000000 |  |  |  | 291000000
|  | 6.B | Design Schematic |  | 0
|  | 6.C | Design Development |  | 0
|  | 6.D | Detail Design & Documentation |  | 0
|  | 6.E | Tender Phrase |  | 0
|  | 6.F | Construction Stage |  | 0
| Maket/Model | 7.A | Maket/Model | 29500000 | 0
| Soil Test | 8.A | Factual Investigation | 170000000 | 12500000 |  |  | 12500000
|  | 8.B | SSRA Study |  | 0
|  | 8.C | Geotechnical Design Report |  | 119000000 |  |  |  | 119000000
|  | 8.D | TPKB Permission Approval |  | 0
| Survey-Topography | 9.A | Topography survey | 35000000 | 0
| Quantity Surveyor | 10.A | Project Consept stage | 1250000000 | 382400000 |  |  |  | 382400000
|  | 10.B | Documentation stage |  | 0
|  | 10.C | Tender phase & Contract Awards |  | 0
|  | 10.D | Monthly Construction phase |  | 0
|  | 10.E | Final Account |  | 0
| Environmental Graphic and Signage | 11.A | Consept Design | 350000000 | 0
|  | 11.B | Planning Development Stage |  | 0
|  | 11.C | Tender Document Stage |  | 0
|  | 11.D | Construction Stage |  | 0
| Special Lighting | 12.A | Design Concept | 275000000 | 55000000 |  |  |  | 55000000
|  | 12.B | Design Development |  | 0
|  | 12.C | Tender Documentation |  | 0
|  | 12.D | Construction administration |  | 0
| Interior | 13.A | Design Concept | 700000000 | 0
|  | 13.B | Design Development |  | 0
|  | 13.C | Tender Documentation |  | 0
|  | 13.D | Construction administration |  | 0
| Green Consultant | 14.A | Schematic design/LEED Core & Shell Pre-certification | 1282500000 | 0
|  | 14.B | Design Development/ LEED design Submission |  | 0
|  | 14.C | Tender Documentation |  | 0
|  | 14.D | Construction Period |  | 0
|  | 14.E | LEED Construction Submission |  | 0
| Interior | 13.A.1 | Design Concept |  | 0
|  | 13.B.1 | Design Development |  | 0
|  | 13.C.1 | Tender Documentation |  | 0
|  | 13.D.1 | Construction administration |  | 0
| Amdal | 14.A.1 | Completion document for Andal, RKL and RPL | 600000000 | 0
|  | 14.B.1 | Completion document legalization for Andal, RKL and RPL |  | 0
| Security and Risk | 15.A | Design Schematic |  | 60000000 |  |  |  | 60000000
|  | 15.B | Design Development |  | 0
|  | 15.C | Detail Design & Documentation |  | 0
| Utility Connection Fee | 16.A | PLN Connection Fee | 5275000000 | 0
|  | 16.B | Telkom Connection Fee |  | 0
| Dirwas | 17.A | Dirwas | 300000000 | 0
| Construction Management | 18.A | Construction Stage | 4500000000 | 0
|  | 18.B | Maintenance Stage |  | 0
| Project Management | 19.A | Personel | 8310000000 | 1806093768.4 |  |  |  | 1806093768.4
|  | 19.B | Operational/Overhead | 3318000000 | 188896864.4 |  | 1615500 | 18919825 | 168361539.4
| Permit and Fee | 20.A | Lulus TPAK |  | 0
|  | 20.B | Revisi BLAD |  | 0
|  | 20.C | SIPPT |  | 0
|  | 20.D | Pelampauan KLB |  | 0
|  | 20.E | Test Pile |  | 0
|  | 20.F | Blok Plan |  | 0
|  | 20.G | IP Struktur |  | 0
|  | 20.H | IMB Definitif |  | 0
|  | 20.I | Revisi Blaad, KDB 30 % dan KLB 3,5 |  | 0
|  | 20.J | Pemecahan Sertipikat |  | 0
|  | 20.K | KRK (Ketetapan Rencana Kota) |  | 0
|  | 20.L | SLF (Sertifikasi Layak Fungsi) |  | 0
|  | 20.M | KKOP (Izin Ketinggian) |  | 0
|  | 20.N | Biaya Notaris |  | 16500000 |  |  |  | 16500000
|  | 20.O | Izin Lain-lain |  | 0
| Retribution Cost | 21.A | IMB |  | 0
|  | 21.B | AMDAL |  | 0
|  | 21.C | JALAN - PU , DISHUB |  | 0
|  | 21.D | PAJAK REKLAME - CONSTRUCTION |  | 0
|  | 21.E | NAME / BRANDING/LOGO/COPYRIGHT |  | 0
| Traffic Study | 22.A | Draft Traffic Study Report |  | 0
|  | 22.B | Final Traffic Study Report |  | 0
Hard Cost | Foundation | 1 | Bored Piles | 19886326000 | 0
| Bulk Excavation | 2 | Excavations and Site Clearance | 2742992000 | 0
| Structural Work | 3 | Substructure and Upper Structure |  | 0
|  | 3.A.1 | Backfilling to make up level | 3000000000 | 0
|  | 3.B.1 | Foundations (pile caps, ground beams & ground slabs). | 26598814000 | 0
|  | 3.C.1 | Basement Structure | 26053685000 | 0
|  | 3.D.1 | Tower Structure | 74375215000 | 0
| Architectural Works | 4 | Architectural Works |  | 0
|  | 4.A.1 | Extenal Wall and Finishes ( brick wall, cement render, painting etc) | 2200854000 | 0
|  | 4.B.1 | Windows and doors | 6722106000 | 0
|  | 4.C.1 | Internal walls and partitons | 3664990000 | 0
|  | 4.D.1 | Wall finishes | 8903902000 | 0
|  | 4.E.1 | External walls and finishing |  | 0
|  | 4.F.1 | Floor finishes | 4358044500 | 0
|  | 4.G.1 | Ceiling finishes | 12848635400 | 0
|  | 4.H.1 | Sanitary appliances | 3001555000 | 0
| Façade | 5 | Façade (Glass, Frame, Sun Shade, ACP) | 33378800000 | 0
| Stone work | 6.A.1 | Wall stone works (Granit and marble) | 2120400000 | 0
|  | 6.B.1 | Floor stone work (Granit and marble) | 4397090000 | 0
| Furniture & Equipement | 7 | Fittings, Furnitures and Equipment (FF&E). | 3817200000 | 0
| Signage | 8 | Signage, Graphics and Function Equipment | 2638694000 | 0
| MEP | 9 | Services |  | 0
|  | 9.A.1 | Plumbing installations. | 13384331900 | 0
|  | 9.B.1 | Fire Protection and Detection | 15970833750 | 0
|  | 9.C.1 | Electrical installations. | 49493255000 | 0
|  | 9.D.1 | Minor Building MEP | 1170232000 | 0
|  | 9.E.1 | External MEP | 1250000000 | 0
| Special Lighting | 10 | Special Lighting | 2500000000 | 0
| MVAC | 11 | Airconditioning and Ventilation | 52523792250 | 0
| Electronic & Security System | 12.A.1 | Communication & security installation | 16752635800 | 0
|  | 12.B.1 | Vertical Transportation Installation |  | 0
| Elevator & Escalator | 13 | Elevator and Escalator | 17840000000 | 0
| Gondola System | 14 | Gondola | 2776000000 | 0
| Genset Installation | 15 | Stanby power generator installations (8000 kVA). | 20680000000 | 0
| Utility | 16.A.1 | PLN electrical supply |  | 0
|  | 16.B.1 | PDAM water supply |  | 0
|  | 16.C.1 | Deep well installations |  | 0
|  | 16.D.1 | Water treatment plant. |  | 0
|  | 16.E.1 | Sewage treatment plant |  | 0
|  | 16.F.1 | Drainage outfall |  | 0
|  | 16.G.1 | TELKOM telephone lines |  | 0
|  | 16.H.1 | Builder's work in connection with utilities. |  | 0
| Infrastructure | 17.A.1 | Minor Building (F & B and Miscelaneous Minor Building) | 4562082200 | 0
|  | 17.B.1 | Covered Way | 1545600000 | 0
|  | 17.C.1 | Hardscaping | 11814780000 | 0
|  | 17.D.1 | Stormwater drainage | 1500000000 | 0
|  | 17.E.1 | Elevated Road |  | 0
| Landscaping | 18 | Softscaping/landscaping | 769180000 | 0
| BWIC and Main Contractor's Attendance | 19 | BWIC and Main Contractor's Attendance | 3877750000 | 0
| Preliminaries | 20 | Preliminaries 6% | 27493186548 | 19500000 |  |  |  | 19500000
| Insurance | 21 | Insurances 0.1% | 485712962.348 | 76532500 |  |  |  | 76532500
| Contingency | 22 | Contingency |  | 0
| PPN | 23 | PPN 10% |  | 0
| Cost Of Fund | 99.A | Bank Interest |  | 0
|  | 99.B | Bank Provision |  | 0
|  | 99.C | Financial Advisor |  | 57500000 |  |  |  | 57500000
|  |  | TOTAL |  | 5542723132.8 | 0 | 1615500 | 31419825 | 5509687807.8 | 0 | 0 | 5542723132.8

## ESTATE
Cost
Grup | Phase | Code | Task | Budget | 2010 | 2011 | 2012 | 2013 | 2014 | 2015
Soft Cost | Feasibility Study | 0.A | Appraisal Work | 1729390000 |  |  | 135000000
|  | 0.B | Feasibility Study | 530000000
| Master Planning | 1.A | Concept and Schematic | 2778313000
| Design Development | 2.A | Consept Design
|  | 2.B | Planning Development Stage | 2120000000
|  | 2.C | Tender Document Stage
|  | 2.D | Construction Stage | 1000000000
| Infrastructure | 3.A | Consept Design
|  | 3.B | Planning Development Stage
|  | 3.C | Tender Document Stage
|  | 3.D | Construction Stage
| Façade | 4.A | Schematic Design Stage
|  | 4.B | Design Developemnt stage
|  | 4.C | Tender Documentation Stage
|  | 4.D | Tender Stage
|  | 4.E | Performance Mock-Up Stage
|  | 4.F | Shop drawing & Engineering Review Stage
|  | 4.G | Fabrication and Installation Stage
|  | 4.H | Hand - Over Stage | 68250000
| Structure and Civil Engineering | 5.A | Consept Design
|  | 5.B | Planning Development Stage
|  | 5.C | Tender Document Stage
|  | 5.D | Construction Stage | 500000000
| Mechanical, Electrical and Plumbing | 6.A | Design Concept
|  | 6.B | Design Schematic
|  | 6.C | Design Development
|  | 6.D | Detail Design & Documentation
|  | 6.E | Tender Phrase
|  | 6.F | Construction Stage | 100000000
| Maket/Model | 7.A | Maket/Model | 310000000
| Soil Test | 8.A | Factual Investigation
|  | 8.B | SSRA Study
|  | 8.C | Geotechnical Design Report
|  | 8.D | TPKB Permission Approval
| Survey-Topography | 9.A | Topography survey | 122960000
| Quantity Surveyor | 10.A | Project Consept stage
|  | 10.B | Documentation stage
|  | 10.C | Tender phase & Contract Awards
|  | 10.D | Monthly Construction phase
|  | 10.E | Final Account | 350000000
| Environmental Graphic and Signage | 11.A | Consept Design
|  | 11.B | Planning Development Stage
|  | 11.C | Tender Document Stage
|  | 11.D | Construction Stage | 275000000
| Special Lighting | 12.A | Design Concept
|  | 12.B | Design Development
|  | 12.C | Tender Documentation
|  | 12.D | Construction administration
| Interior | 13.A | Design Concept
|  | 13.B | Design Development
|  | 13.C | Tender Documentation
|  | 13.D | Construction administration | 2000000000
| Green Consultant | 14.A | Schematic design/LEED Core & Shell Pre-certification
|  | 14.B | Design Development/ LEED design Submission
|  | 14.C | Tender Documentation
|  | 14.D | Construction Period
|  | 14.E | LEED Construction Submission
| Interior | 13.A.1 | Design Concept
|  | 13.B.1 | Design Development
|  | 13.C.1 | Tender Documentation
|  | 13.D.1 | Construction administration | 1000000000
| Amdal | 14.A.1 | Completion document for Andal, RKL and RPL
|  | 14.B.1 | Completion document legalization for Andal, RKL and RPL
| Security and Risk | 15.A | Design Schematic
|  | 15.B | Design Development
|  | 15.C | Detail Design & Documentation
| Utility Connection Fee | 16.A | PLN Connection Fee
|  | 16.B | Telkom Connection Fee
| Dirwas | 17.A | Dirwas
| Construction Management | 18.A | Construction Stage
|  | 18.B | Maintenance Stage
| Project Management | 19.A | Personel
|  | 19.B | Operational/Overhead
| Permit and Fee | 20.A | Lulus TPAK | 5400000000
|  | 20.B | Revisi BLAD | 700000000
|  | 20.C | SIPPT | 500000000
|  | 20.D | Pelampauan KLB
|  | 20.E | Test Pile | 700000000
|  | 20.F | Blok Plan
|  | 20.G | IP Struktur | 800000000
|  | 20.H | IMB Definitif
|  | 20.I | Revisi Blaad, KDB 30 % dan KLB 3,5
|  | 20.J | Pemecahan Sertipikat
|  | 20.K | KRK (Ketetapan Rencana Kota)
|  | 20.L | SLF (Sertifikasi Layak Fungsi) | 400000000
|  | 20.M | KKOP (Izin Ketinggian) | 16500000
|  | 20.N | Biaya Notaris | 1856000000
|  | 20.O | Izin Lain-lain | 7004775000
| Retribution Cost | 21.A | IMB | 500000000
|  | 21.B | AMDAL | 1000000000
|  | 21.C | JALAN - PU , DISHUB | 300000000
|  | 21.D | PAJAK REKLAME - CONSTRUCTION | 50000000
|  | 21.E | NAME / BRANDING/LOGO/COPYRIGHT | 249100000
| Traffic Study | 22.A | Draft Traffic Study Report
|  | 22.B | Final Traffic Study Report
Hard Cost | Foundation | 1 | Bored Piles
| Bulk Excavation | 2 | Excavations and Site Clearance
| Structural Work | 3 | Substructure and Upper Structure
|  | 3.A.1 | Backfilling to make up level
|  | 3.B.1 | Foundations (pile caps, ground beams & ground slabs).
|  | 3.C.1 | Basement Structure
|  | 3.D.1 | Tower Structure
| Architectural Works | 4 | Architectural Works
|  | 4.A.1 | Extenal Wall and Finishes ( brick wall, cement render, painting etc)
|  | 4.B.1 | Windows and doors
|  | 4.C.1 | Internal walls and partitons
|  | 4.D.1 | Wall finishes
|  | 4.E.1 | External walls and finishing
|  | 4.F.1 | Floor finishes
|  | 4.G.1 | Ceiling finishes
|  | 4.H.1 | Sanitary appliances
| Façade | 5 | Façade (Glass, Frame, Sun Shade, ACP)
| Stone work | 6.A.1 | Wall stone works (Granit and marble)
|  | 6.B.1 | Floor stone work (Granit and marble)
| Furniture & Equipement | 7 | Fittings, Furnitures and Equipment (FF&E).
| Signage | 8 | Signage, Graphics and Function Equipment
| MEP | 9 | Services
|  | 9.A.1 | Plumbing installations.
|  | 9.B.1 | Fire Protection and Detection
|  | 9.C.1 | Electrical installations.
|  | 9.D.1 | Minor Building MEP
|  | 9.E.1 | External MEP
| Special Lighting | 10 | Special Lighting
| MVAC | 11 | Airconditioning and Ventilation
| Electronic & Security System | 12.A.1 | Communication & security installation
|  | 12.B.1 | Vertical Transportation Installation
| Elevator & Escalator | 13 | Elevator and Escalator
| Gondola System | 14 | Gondola
| Genset Installation | 15 | Stanby power generator installations (8000 kVA).
| Utility | 16.A.1 | PLN electrical supply
|  | 16.B.1 | PDAM water supply
|  | 16.C.1 | Deep well installations
|  | 16.D.1 | Water treatment plant.
|  | 16.E.1 | Sewage treatment plant
|  | 16.F.1 | Drainage outfall
|  | 16.G.1 | TELKOM telephone lines
|  | 16.H.1 | Builder's work in connection with utilities.
| Infrastructure | 17.A.1 | Minor Building (F & B and Miscelaneous Minor Building)
|  | 17.B.1 | Covered Way
|  | 17.C.1 | Hardscaping
|  | 17.D.1 | Stormwater drainage
|  | 17.E.1 | Elevated Road
| Landscaping | 18 | Softscaping/landscaping
| BWIC and Main Contractor's Attendance | 19 | BWIC and Main Contractor's Attendance
| Preliminaries | 20 | Preliminaries 6%
| Insurance | 21 | Insurances 0.1%
| Contingency | 22 | Contingency
| PPN | 23 | PPN 10%
| Cost Of Fund | 99.A | Bank Interest
|  | 99.B | Bank Provision
|  | 99.C | Financial Advisor